# EXHIBIT C-6

STATEMENT OF WORK

# IPAAS PROJECT MANAGEMENT SOW

This Exhibit C-6 Statement of Work (“C-6 SOW”) is entered into as of January 1, 2026 (the “C-6 SOW Effective Date”) by and between:

| Party | Legal Name | Jurisdiction / Address |
| --- | --- | --- |
| Provider | SALVE, INC. | Wyoming corporation 1110 Brickell Avenue #400-89, Miami, FL 33131 |
| Customer | STORY COMPANIES LLC | 120 N. 44th Street, Suite 410, Phoenix, Arizona 85034, USA |

Provider and Customer are each a “Party” and together the “Parties.” This C-6 SOW is entered into pursuant to the terms and conditions of the Software as a Service Agreement between the Parties dated April 3, 2025 (the “Agreement”) and issued under the Exhibit A-3 Purchase Order dated January 1, 2026 (the “Exhibit A-3 Purchase Order”). For purposes of clarity, the Agreement, this C-6 SOW, and the Exhibit A-3 Purchase Order are collectively referred to as the “Agreement.”

Capitalized terms used but not defined in this C-6 SOW shall have the meanings given to them in the Agreement. In the event of a conflict between the terms of this C-6 SOW and the Agreement (or any other C-6 SOW), the terms of the Agreement shall control, unless expressly stated otherwise in this C-6 SOW or the Agreement, and solely with respect to the Services provided under this C-6 SOW.

## PROJECT OVERVIEW

Relationship to C-5 iPaaS SOW: This C-6 PM SOW provides project management, governance, and coordination services specifically for the iPaaS implementation work being performed under the C-5 iPaaS SOW. The Project Manager and project administration resources provided under this C-6 SOW will be responsible for managing the overall implementation timeline, coordinating deliverables across the Integrations and Flows specified in Exhibit D, facilitating stakeholder communication, and managing the Change Order process. Customer has separately engaged Provider for the technical implementation work (integration setup, connector development, Flow creation, testing, and deployment) under the C-5 iPaaS SOW. The fees under this C-6 PM SOW are in addition to, not duplicative of, the fees charged under the C-5 SOW.

  - Purpose

This Statement of Work (SOW) defines the scope of Project Management and Governance Services provided by the Provider to oversee the technical delivery of the iPaaS implementation defined in the C-5 iPaaS SOW Implementation.

  - Background

The Customer acknowledges the inherent complexity and cross-functional nature of the technical initiatives outlined in the C-5 SOW, including the integration of ten (10) third-party technologies and the coordination of requirements across multiple Customer department leads (Finance, Retail, Marketing, Wholesale, Procurement, and Supply Chain). The success of this project requires dedicated, experienced oversight to ensure technical deliverables are met on time and on target. This Project Management SOW is established to provide the necessary structure, coordination, and proactive management required to timely deliver the technical milestones aligned with the Customer’s critical 2026 Technological Roadmap.

## KEY DEFINITIONS

For the purposes of this SOW, the following definitions apply:

- “Customer” means the entity receiving the Services.

- “Provider” means the entity performing the Services.

- “iPaaS” means Integration Platform as a Service; the cloud-based platform used to develop, deploy, and manage the Flows.

- “Integrations” refer collectively to the third-party technologies and systems listed in the C-5 iPaaS SOW.

- “Flows” mean the data and process workflows developed by the Provider using the Provider's iPaaS platform to connect two or more of the enabled Integrations.

- “User Acceptance Testing” or “UAT” mean the formal process where the Customer validates that the Integrations meet the specified business requirements before deployment to Production.

- SOW Effective Date: The date upon which both the Customer and the Provider have executed this SOW, signifying the official project start.

- “Engagement Term” The duration of the services provided under this C-6 SOW, as specified in the Exhibit A-3 Purchase Order dated January 1, 2026.

- “Deliverables” mean the work product listed in Section 6 hereto.

- “Services” mean the activities described in Section 3 hereto.

- “Work Product” means reports, analyses, roadmaps, prototypes, and other materials produced for Customer under this C-6 SOW.

- “Steering Committee” means the senior individuals designated by the Customer who are responsible for the administrative and operational oversight of the Project and ensuring the Customer fulfills all responsibilities outlined in this SOW.

- “Change Order” or “CO” means the formal written agreement required to authorize any alteration, addition, or deletion to the scope of work, pricing, deliverables, or schedule of this C-6 SOW, the C-5 iPaaS SOW Implementation, or the Exhibit D: 2026 Technical Roadmap spreadsheet.

## SCOPE OF SERVICES

  - Project Governance & Structure

- Establish and lead a formal project Steering Committee.

- Define communication protocols and meeting cadences (weekly stand-ups, weekly status reports, weekly steering calls) subject to change month-over-month.

  - Planning & Scheduling

- Creation and maintenance of the master project schedule, integrating technical tasks from the Implementation SOW with Customer responsibilities.

- Proactive management of dependencies and critical path tasks.

  - Risk & Issue Management

- Develop and maintain project risk logs by department.

- Lead department meetings to identify, prioritize, and assign owners for all project tasks and identify any potential issues.

  - Scope & Change Management

- Execution of the formal Change Management Process defined below.

- Ensure all new requests are properly documented with the project management team, assessed for impact, and approved by the steering committee.

  - Project Update Reporting

- Provide bi-weekly status reports detailing progress against milestones, timeline, and upcoming project needs.

## DELIVERABLES & MILESTONES

These are the tangible documents and meetings produced and managed by the Project Management team under this C-6 SOW.

| Deliverable | Description | Cadence |
| --- | --- | --- |
| Master Project Schedule | The definitive, living schedule tracking all tasks, milestones, and dependencies across both the technical implementation and Customer-side responsibilities. Contractually references and is maintained weekly based on the data within Exhibit D: 2026 Technical Roadmap Spreadsheet. | Maintained Weekly |
| Formal Change Order Log | Document of record for all scope change requests, including authorization status, associated project impacts, and timeline adjustments. | Maintained As Needed |
| Project Status Reports | Weekly written summary detailing progress against the schedule, resource consumption, deliverable status, and overall project health (R/A/G status). | Bi-weekly (sent via email to the Project Steering Committee) |
| Risk and Issue Log | Formal log tracking all identified risks (potential issues) and active issues (current roadblocks), categorized and assigned owners by department. | Maintained Weekly |
| Executive Steering Committee Meetings | Formal, live review meeting providing high-level project status, risk escalation, and opportunities for the Project Steering Committee to provide strategic direction, feedback, and authorization for critical adjustments (e.g., Change Orders). | Scheduled by request (typically Monthly or Bi-Weekly) |

## ROLES & RESPONSIBILITIES

This section defines the division of effort required to successfully deliver the Integrations and Flows and meet the milestones defined in Exhibit D: Integrated Roadmap.

  - Provider Responsibilities

The Provider is responsible for the following regarding the implementation of the C-5 iPaaS SOW.

| Phase | Responsibility | Detail |
| --- | --- | --- |
| I. Requirements & Design | Project Cadence | Define, own, and maintain the overall project timeline and meeting cadence. Issue requests for scheduling and proactively track progress against the master schedule (Exhibit C). |
|  | iPaaS Setup & Enablement | Configure and provision the dedicated development, UAT, and production iPaaS environments and enable all 10 third-party Integrations (connectors, security, and networking). |
|  | Documentation | Draft the Integration and Flow Design Documents based on customer input. |
| II. Implementation & Development | Flow Implementation | Perform the hands-on development (coding, configuration) of the Flows based on the requirements gathered from department discovery. |
|  | Unit Testing | Conduct comprehensive internal unit testing and technical validation of all implemented Flows. |
| III. Testing & Acceptance | UAT Environment Prep | Promote tested Flows to the UAT environment and prepare the test datasets necessary for customer validation. |
|  | Issue Support & Defect Resolution | Provide active support and root cause analysis during the UAT cycle, and resolve defects found that are attributable to errors in the Flow implementation. |
|  | Deployment | Execute the final deployment of the Flows into the Production environment upon receipt of Customer Sign-off. |
|  | Knowledge Transfer | Deliver final project documentation and technical training to the Customer's designated internal team on the management and monitoring of the deployed Flows. |

    - Provider POCs

The Provider shall assign the following team members for the duration of the engagement, who will serve as the main POCs:

| Department | POC Name | POC Email |
| --- | --- | --- |
| Lead Engineer | Justin Zablocki | Justin@getsalve.co |
| Lead Analyst | Tony Richards | Tony@getsalve.co |
| Project Management | Erin Haden | Erin@getsalve.co |
| Project Administrator | Niki Rogers | Niki@getsalve.co |
| Head of Support | Madison Persyn | Madison@getsalve.co |

  - Customer Responsibilities

The Customer is responsible for the following regarding the implementation of the C-5 iPaaS SOW.

| Phase | Responsibility | Detail |
| --- | --- | --- |
| I. Requirements & Design | Project Oversight | Designate a Steering Committee to serve as primary points of contact and decision-makers. |
|  | System Access | Timely provision of all required system access, API keys, credentials, and firewall exceptions to the Provider. |
|  | Requirements Review & Sign-Off | Be available for review sessions to define and quickly sign-off on the Flow requirements or formally request changes. |
|  | Scheduling Compliance | Respond promptly to all scheduling requests from the Provider and ensure Department Leads are available for all scheduled meetings (design, review, UAT) to keep the project on time and target. Provider will give as much lead time as possible to make these scheduling requests. |
| II. Implementation & Development | Resource Availability | Ensure Department Leads and subject matter experts are available for clarifications during development. |
|  | Internal Coordination | Manage internal dependencies and coordinate with the 10 third-party technology owners for access changes. |
|  | Internal Documentation | Create and maintain all internal Standard Operating Procedures (SOPs) and workflow documentation for their teams, reflecting changes introduced by the new Flows. |
| III. Testing & Acceptance | UAT Participation & Edge Case Validation | Dedicate necessary resources to actively and fully participate in Quality Assurance (QA) and User Acceptance Testing (UAT) using scenarios relevant to the department's normal operations. |
|  | Critical Feedback (SLA Mandate) | Properly notify the Provider immediately of any existing or anticipated issues within the Customer's normal workflow or application setup that would impede Flow success. Proper notification must happen within the approved SLA support channels. |
|  | Final Sign-Off & Acceptance | Provide formal written acceptance (UAT and Go-Live Acceptance) that all Flows are working correctly and meet the defined requirements, authorizing the Production Go-Live. |
|  | Post Go-Live Support | Assume responsibility for the ongoing support of internal teams and operational management. Any necessary maintenance, error resolution, or support required after the warranty period must be initiated through the approved SLA support channels. |

    - Customer POCs

The Customer designates the following individuals as department-specific Points of Contact (POC). These POCs will be responsible for facilitating communication, sharing relevant information, and providing timely feedback within their respective departments.

STEERING COMMITTEE POCs

| Department | POC Name | POC Email |
| --- | --- | --- |
| VP and Controller | Dan Mandel | dmandel@storypartners.com |
| Director of IT | Trevor Abney | tabney@storypartners.com |
| Chief of Staff | Andrea Bagneschi | abagneschi@storypartners.com |
| EVP of Operations | Bill Sullivan | bsullivan@storypartners.com |
| Corporate PM | Diana Wacholz | dwacholz@storypartners.com |

FINANCE POCs

| Department | POC Name | POC Email |
| --- | --- | --- |
| VP and Controller | Dan Mandel | dmandel@storypartners.com |
| EVP Finance | Jeremy DePeters | jdepeters@storypartners.com |
| Director of Accounting Operations | Mostafa Al Mukhtar | mmukhtar@storypartners.com |

MARKETING POCs

| Department | POC Name | POC Email |
| --- | --- | --- |
| VP of Marketing | Aaron Dubois | adubois@storypartners.com |
| Director of CRM | Erin Rosen | erosen@storypartners.com |

RETAIL POCs

| Department | POC Name | POC Email |
| --- | --- | --- |
| Retail Operations Director | Kristal Royal | kroyal@storypartners.com |
| VP of Retail | Lan Northington | anorthington@storypartners.com |

WHOLESALE POCs

| Department | POC Name | POC Email |
| --- | --- | --- |
| National Wholesale Director | Jason Gully | jgully@storypartners.com |

SUPPLY CHAIN POCs

| Department | POC Name | POC Email |
| --- | --- | --- |
| VP of Supply Chain | Matthew Mueller | Mmueller@storypartners.com |

CULTIVATION POCs

| Department | POC Name | POC Email |
| --- | --- | --- |
| VP of Cultivation | Egan O’Keefe | eokeefe@storypartners.com |

## TIMELINE, PRICING AND PAYMENT TERMS

  - Project Timeline

The total estimated project duration is Twelve (12) Months (the Engagement Term), beginning on the SOW Effective Date and concluding twelve months thereafter. The phasing and specific milestone completion dates are dictated by the priorities and targets set forth in Exhibit C: 2026 Technical Roadmap Spreadsheet. This timeline is constructed to ensure all necessary Flows are implemented and deployed to support the critical Pilot Store Launch Milestone in April 2026.

  - Pricing Structure (Integration-Based Model)

The Provider shall deliver project management and governance services for a fixed monthly retainer for the duration of the agreed-upon Engagement Term.

| Pricing Model | Frequency | Fixed Retainer Cost (Monthly) | Allotted Hours (Monthly) | Total Cost (12 Months) |
| --- | --- | --- | --- | --- |
| Fixed Retainer | Monthly | $20,000.00 | 80 hours | $240,000.00 |

  - Disclaimer on Continuing Services

The fixed monthly retainer and associated total cost covers the Project Management and governance Services solely for the 12-month Engagement Term defined herein. Any additional Project Management or Governance services related to the C-5 iPaaS SOW Implementation or this C-6 SOW that may be required in 2027 or beyond must be formalized and agreed upon by both Parties under a separate, continuing Statement of Work.

  - Fee Inclusion

The Fixed Retainer covers the labor cost for the Project Management activities defined in Section 3 (Scope of Services) including the creation of all required deliverables (Master Schedule, Status Reports, Logs, and meeting coordination).

  - Over-Allocation (Time & Materials)

- The services are structured around a maximum allocation of 80 hours per month (20 hours per week).

- Should the Customer require services exceeding the 80 allotted hours in any given month, the Provider will notify the Customer immediately.

- Work exceeding the allotted hours will be subject to a formal Change Order and billed at the Provider's standard Time & Materials (T&M) rate of [$250] per hour.

  - Payment Terms

Suspension of Services for Non-Payment: In the event Customer fails to pay any undisputed invoice within forty-five (45) days of the invoice date (i.e., 15 days past the Net 30 due date), Provider may, in its sole discretion and without liability, suspend or withhold: (a) performance of ongoing Services under this SOW; (b) delivery of completed or in-progress deliverables; (c) project management meetings, status calls, and training sessions; and (d) commencement of any new work. Provider shall provide Customer with written notice at least five (5) business days prior to implementing any such suspension. Upon Customer's payment in full of all overdue amounts plus accrued interest, Provider shall resume suspended Services within two (2) business days. Any delays in project timelines caused by suspension shall extend all milestone dates by the duration of the suspension period.

Invoices for the fixed monthly retainer shall be issued on the 1st of each month in advance for that month's services (i.e., the January retainer will be invoiced on January 1st). All invoices issued under this C-6 SOW are subject to the payment terms set forth in the Exhibit A-3 Purchase Order: Net 30, with a 15-day grace period during which late fees will not apply. Unpaid invoices beyond Net 45 shall accrue interest at one (1%) percent APR on all amounts unpaid until all balances are satisfied. For the first month of services, if the C-6 SOW Effective Date is not the 1st of the month, the initial invoice will be prorated based on the number of days remaining in that month, and the 80-hour monthly allocation will be prorated proportionally. Any services provided pursuant to a Change Order for time and materials exceeding the 80-hour monthly allocation shall be invoiced in the month following the month in which such overage services were performed, with payment due under the same Net 30 / Grace 15 / Net 45 structure.

## CHANGE MANAGEMENT PROCESS

For complete Change Management Process procedures, refer to Section 10 of the C-5 iPaaS SOW, which governs change control for both the iPaaS implementation and the Project Management services under this C-6 SOW. The procedures set forth in C-5 Section 10 are hereby incorporated by reference into this C-6 SOW. The following provisions supplement the C-5 Change Management Process specifically for Project Management services:

The purpose of this process is to formally manage and authorize any requested change to the scope of services, pricing, deliverables, or schedule of this C-6 SOW, or the underlying C-5 iPaaS SOW. Any such requests must be handled via a formal Change Order (CO).

  - Initiation

    - Request Submission

The requesting party (Customer or Provider) shall submit a written request to the Project Management team (Provider project manager and project administrator) detailing the necessity, scope, and anticipated impact of the change.

    - Required Documentation:

The request must clearly outline:

- The reason for the change.

- The specific items in the Exhibit D: 2026 Technical Roadmap Spreadsheet that will be affected.

- The required new deliverable or alteration to an existing Flow.

  - Impact Assessment

    - Provider Assessment

The Provider shall assess the request and document the full impact on the project, including changes to cost, resource considerations, and the roadmap schedule defined in Exhibit D.

    - Review

The assessment, along with the proposed solution, will be reviewed with the Steering Committee during the Executive Steering Committee Meetings.

  - Authorization and Execution

    - Authorization

The Change Order document must be signed and authorized by the Steering Committee from both the Customer and the Provider before any work related to the change can commence.

    - Logging

Once authorized, the change is formally recorded in the Formal Change Order Log and integrated into the Master Project Schedule.

[Signature page to follow]

### IN WITNESS WHEREOF, the Parties have caused this Agreement to be executed by their duly authorized representatives as of the Effective Date and may be executed in counterparts, each of which is deemed an original with electronic signatures being binding and enforceable on the Parties.

| SALVE, INC. | STORY COMPANIES LLC |
| --- | --- |
| By: __________________________ | By: ___________________________ |
| Name: Nicole Rogers | Name: Andrea Bagneschi |
| Title: CEO | Title: Chief of Staff |
| Date: _________________________ | Date: _________________________ |